## Workflow
Workflow Issue Types
Epic | Epic 1 | Login Functionality | scrum master
Story | Story | UI | Developer 1 | Estimate - at story level only | Swati
Defect | Task 1 | UI | Developer 1 |  | Swati
Task | Task 2 | UI | Developer 1 |  | Swati
| Defect 1 |  | Developer 2 |  | Suvendu
| Story | BE | Developer 2
| Story | Intergration | Developer 3

## Story
From | Owner | Transition |  | To | Assignee | Comments
OPEN | PO/ Scrum Master | Close | → | CLOSED | PO
|  | Drop | → | DROPPED
|  | Put On Hold | → | ON HOLD
|  | Need More Info | → | MORE INFO
|  | Requirement Signed Off | → | REQUIREMENT SIGNED OFF
Ready For Grooming | PO/ Scrum Master | Close | → | CLOSED | PO | 1 week before the sprint start, we should be clear about all the requirements. Move only those tickets where requirements are clear.
|  | Drop | → | DROPPED | PO
|  | Put on Hold | → | ON HOLD | PO
|  | Need More Info | → | MORE INFO | PO
|  | Ready for Sprint Planning | → | READY FOR SPRINT PLANNING | PO/ Scrum master
READY FOR SPRINT PLANNING | Scrum Master | In Sprint | → | In Sprint | Scrum Master | 1 day before sprint starts
|  | Close | → | CLOSED | Need discussion with PO, and assign to PO, developer can’t close | stories having clarity on req will move to sprint planning
|  | Drop | → | DROPPED | Need discussion with PO, and assign to PO, developer can’t drop | Estimation in sprint planning
|  | Put on Hold | → | ON HOLD | PO/ Developer/ scrum master
|  | Need More Info | → | MORE INFO | PO
In Sprint | Scrum Master | Start Analysis | → | IN ANALYSIS | Developer
|  | Start Development | → | IN DEVELOPMENT | Developer
|  | Close | → | CLOSED | Need discussion with PO, and assign to PO, developer can’t close
|  | Drop | → | DROPPED | Need discussion with PO, and assign to PO, developer can’t close
|  | Put on Hold | → | ON HOLD
|  | Need More Info | → | MORE INFO | PO / Scrum Master
IN ANALYSIS | Developer | Start Development | → | IN DEVELOPMENT | Developer
|  | Need More Info | → | MORE INFO | PO
|  | Close | → | CLOSED | Need discussion with PO, and assign to PO, developer can’t close
|  | Drop | → | DROPPED | Need discussion with PO, and assign to PO, developer can’t drop
|  | Put on Hold | → | ON HOLD | POD Lead/ scrum master/PO/ Developer
| PO | Reopen | → | OPEN | Developer
IN DEVELOPMENT | Developer | More Analysis req. | → | In Analysis | Developer
|  | Ready for Testing | → | READY FOR TESTING | Developer
|  | Need More Info | → | MORE INFO | PO
|  | Dropped | → | DROPPED | Need discussion with PO, and assign to PO, developer can’t drop
|  | Put On Hold | → | ON HOLD | Need discussion with PO, and assign to PO, developer can’t on hold
|  | Reopen | → | OPEN | Developer
|  | Close | → | CLOSED | Need discussion with PO, and assign to PO, developer can’t close
READY FOR TESTING | Developer | Start Testing | → | IN TESTING | Developer
|  | Start Development | → | IN DEVELOPMENT | Developer
|  | Need More Info | → | MORE INFO | PO
|  | Drop | → | DROPPED | Need discussion with PO, and assign to PO, developer can’t drop
|  | Put On Hold | → | ON HOLD | Need discussion with PO, and assign to PO, developer can’t Hold
|  | Reopen | → | OPEN | NA
|  | Close | → | CLOSED | Need discussion with PO, and assign to PO, developer can’t Close
IN TESTING | Developer | Ready for Sign-off | → | READY FOR SIGN-OFF | PO
|  | Ready for Testing | → | READY FOR TESTING | Developer
|  | Start Development | → | IN DEVELOPMENT | Developer | when deployment is done developer will move to In Testing
|  | Drop | → | DROPPED | Need discussion with PO, and assign to PO, developer can’t Close
|  | Put On Hold | → | ON HOLD | Need discussion with PO, and assign to PO, developer can’t Close
|  | Need More Info | → | MORE INFO | PO
| PO | Reopen | → | OPEN | Developer
| PO | Close | → | CLOSED | PO
DROPPED | Po | Reopen | → | OPEN | Developer
ON HOLD | PO | Start Analysis | → | IN ANALYSIS | Developer
|  | Start Development | → | IN DEVELOPMENT | Developer
|  | Start Testing | → | IN TESTING | Developer
|  | Ready for Testing | → | READY FOR TESTING | Developer
|  | Need More Info | → | MORE INFO | PO
|  | Ready for Sign-off | → | READY FOR SIGN-OFF | PO
|  | Sign-off | → | READY FOR DELIVERY | PO
|  | Reopen | → | OPEN | Developer
MORE INFO | PO | Start Analysis | → | IN ANALYSIS | Developer
|  | Start Development | → | IN DEVELOPMENT | Developer
|  | Ready for Testing | → | READY FOR TESTING | Developer
|  | Start Testing | → | IN TESTING | Developer
|  | Ready for Sign-off | → | READY FOR SIGN-OFF | PO
|  | Sign-off | → | READY FOR DELIVERY | PO
|  | Close | → | CLOSED | PO
|  | Put on Hold | → | ON HOLD | PO
READY FOR SIGN-OFF | PO | Sign-off | → | READY FOR DELIVERY | PO
|  | Reject | → | IN ANALYSIS
|  | Need More Info | → | MORE INFO
|  | Put On Hold | → | ON HOLD
|  | Reopen | → | OPEN
CLOSED | PO | Reopen | → | OPEN | Developer / PO*depending upon the stage of story

## Task
From | Transition |  | To
OPEN | Start Progress | → | IN PROGRESS
| Put on Hold | → | ON HOLD
| Close | → | CLOSED
CLOSED | Reopen | → | OPEN

## Defect
From | Transition |  | To
OPEN | Start Analysis | → | IN ANALYSIS
| Start Development | → | IN DEVELOPMENT
| Close | → | CLOSED
| Drop | → | DROPPED
| Put On Hold | → | ON HOLD
| Need More Info | → | MORE INFO
CLOSED | Reopen | → | OPEN
IN ANALYSIS | Start Development | → | IN DEVELOPMENT
| Ready for Testing | → | READY FOR TESTING
| Need More Info | → | MORE INFO
| Close | → | CLOSED
| Drop | → | DROPPED
| Put on Hold | → | ON HOLD
| Reopen | → | OPEN
IN DEVELOPMENT | Ready for Testing | → | READY FOR TESTING
| Need More Info | → | MORE INFO
| Dropped | → | DROPPED
| Put On Hold | → | ON HOLD
| Reopen | → | OPEN
| Close | → | CLOSED
READY FOR TESTING | Start Testing | → | IN TESTING
| Start Development | → | IN DEVELOPMENT
| Need More Info | → | MORE INFO
| Drop | → | DROPPED
| Put On Hold | → | ON HOLD
| Reopen | → | OPEN
| Close | → | CLOSED
IN TESTING | Ready for Sign-off | → | READY FOR SIGN-OFF
| Ready for Testing | → | READY FOR TESTING
| Start Development | → | IN DEVELOPMENT
| Drop | → | DROPPED
| Put On Hold | → | ON HOLD
| Need More Info | → | MORE INFO
| Reopen | → | OPEN
| Close | → | CLOSED
READY FOR SIGN-OFF | Sign-off | → | READY FOR DELIVERY
| Reject | → | IN ANALYSIS
| Need More Info | → | MORE INFO
| Put On Hold | → | ON HOLD
| Reopen | → | OPEN
DROPPED | Reopen | → | OPEN
ON HOLD | Start Analysis | → | IN ANALYSIS
| Start Development | → | IN DEVELOPMENT
| Start Testing | → | IN TESTING
| Ready for Testing | → | READY FOR TESTING
| Need More Info | → | MORE INFO
| Ready for Sign-off | → | READY FOR SIGN-OFF
| Sign-off | → | READY FOR DELIVERY
| Reopen | → | OPEN
MORE INFO | Start Analysis | → | IN ANALYSIS
| Start Development | → | IN DEVELOPMENT
| Ready for Testing | → | READY FOR TESTING
| Start Testing | → | IN TESTING
| Ready for Sign-off | → | READY FOR SIGN-OFF
| Sign-off | → | READY FOR DELIVERY
| Close | → | CLOSED
| Put on Hold | → | ON HOLD

## update in JIRA workflow - req (hidden)
From | Transition |  | To | Update needed
REQUIREMENT SIGNED OFF | Close | → | CLOSED | Remove
| Drop | → | DROPPED | Remove
| Put on Hold | → | ON HOLD | Remove
| Need More Info | → | MORE INFO | Remove
| Ready for Sprint Planning | → | READY FOR SPRINT PLANNING | Remove
READY FOR SPRINT PLANNING | Start Analysis | → | IN ANALYSIS | Remove
| In Sprint | → | In Sprint | Add
| Close | → | CLOSED
| Drop | → | DROPPED
| Put on Hold | → | ON HOLD
| Need More Info | → | MORE INFO
In Sprint | Start Analysis | → | IN ANALYSIS | Add
| Start Development | → | IN DEVELOPMENT | Add
| Close | → | CLOSED | Add
| Drop | → | DROPPED | Add
| Put on Hold | → | ON HOLD | Add
| Need More Info | → | MORE INFO | Add
IN ANALYSIS | Start Development | → | IN DEVELOPMENT
| Ready for Testing | → | READY FOR TESTING | Remove
| Need More Info | → | MORE INFO
| Close | → | CLOSED
| Drop | → | DROPPED
| Put on Hold | → | ON HOLD
| Reopen | → | OPEN
IN DEVELOPMENT | More Analysis req. | → | In Analysis | Add
| Ready for Testing | → | READY FOR TESTING
| Need More Info | → | MORE INFO
| Dropped | → | DROPPED
| Put On Hold | → | ON HOLD
| Reopen | → | OPEN
| Close | → | CLOSED
READY FOR DELIVERY | Close | → | CLOSED | Remove
| Need More Info | → | MORE INFO | Remove
| Put On Hold | → | ON HOLD | Remove
| Reopen | → | OPEN | Remove
Ready For Grooming | Close | → | CLOSED | Add
| Drop | → | DROPPED | Add
| Put on Hold | → | ON HOLD | Add
| Need More Info | → | MORE INFO | Add
| Ready for Sprint Planning | → | READY FOR SPRINT PLANNING | Add